## Sprint
[5 empty] | Week #1 (16 hrs / week) | [6 empty] | Week #2 (16 hrs / week) | [6 empty] | Week #3 (16 hrs / week) | [6 empty] | Week #4 (16 hrs / week) | [6 empty] | Week #5 (16 hrs / week) | [6 empty] | Week #6 (16 hrs / week) | [6 empty] | Week #7 (16 hrs / week) | [6 empty] | Week #8 (16 hrs / week) | [6 empty] | Week #9 (16 hrs / week) | [6 empty] | Week #10 (16 hrs / week)
Backlog Item | Task |  | Task Owner | Initial Estimate (Total Sprint Hours = 16 x 10) | D1 | D2 | D3 | D4 | D5 | D6 | D7 | D8 | D9 | D10 | D11 | D12 | D13 | D14 | D15 | D16 | D17 | D18 | D19 | D20 | D21 | D22 | D23 | D24 | D25 | D26 | D27 | D28 | D15 | D16 | D17 | D18 | D19 | D20 | D21 | D22 | D23 | D24 | D25 | D26 | D27 | D28 | D15 | D16 | D17 | D18 | D19 | D20 | D21 | D22 | D23 | D24 | D25 | D26 | D27 | D28 | D15 | D16 | D17 | D18 | D19 | D20 | D21 | D22 | D23 | D24 | D25 | D26 | D27 | D28
 | time axis 2020-09-27 to 2020-12-05
[5 empty] | 160 | 157.7143 | 155.4286 | 153.1429 | 150.8571 | 148.5714 | 146.2857 | 144 | 141.7143 | 139.4286 | 137.1429 | 134.8571 | 132.5714 | 130.2857 | 128 | 125.7143 | 123.4286 | 121.1429 | 118.8571 | 116.5714 | 114.2857 | 112 | 109.7143 | 107.4286 | 105.1429 | 102.8571 | 100.5714 | 98.2857 | 96 | 93.7143 | 91.4286 | 89.1429 | 86.8571 | 84.5714 | 82.2857 | 80 | 77.7143 | 75.4286 | 73.1429 | 70.8571 | 68.5714 | 66.2857 | 64 | 61.7143 | 59.4286 | 57.1429 | 54.8571 | 52.5714 | 50.2857 | 48 | 45.7143 | 43.4286 | 41.1429 | 38.8571 | 36.5714 | 34.2857 | 32 | 29.7143 | 27.4286 | 25.1429 | 22.8571 | 20.5714 | 18.2857 | 16 | 13.7143 | 11.4286 | 9.1429 | 6.8571 | 4.5714 | 2.2857 | Ideal Burndown
|  |  |  | 160 | 160 | 160 | 159 | 155 | 151 | 147 | 145 | 145 | 142 | 140 | 139 | 138 | 136 | 129 | 129 | 127 | 125 | 123 | 121 | 117 | 113 | 113 | 111 | 111 | 109 | 106 | 104 | 98 | 98 | 98 | 90 | 88 | 86 | 82 | 82 | 82 | 78 | 72 | 70 | 70 | 65 | 65 | 65 | 63 | 57 | 56 | 52 | 50 | 46 | 46 | 43 | 41 | 39 | 37 | 35 | 33 | 31 | 29 | 27 | 23 | 23 | 19 | 15 | 14 | 11 | 11 | 10 | 8 | 2 | 0 | Remaining Hrs (Total)
Documentation | Create the Class Diagram |  | Apoorv , Pranjay | 1 | bar: 2020-09-29
| Create Project TaskBoard with known Tasks on GitHub |  | Swapnil | 2 | bar: 2020-10-07; 2020-12-04
| Create Architecture Diagram |  | Pranav | 1 | bar: 2020-09-30
| Maintain SCRUM sheet |  | Swapnil | 4 | bar: 2020-10-01; 2020-10-10; 2020-10-24; 2020-11-16
| Create README file |  | Apoorv ,Swapnil | 3 | bar: 2020-09-30; 2020-11-11; 2020-12-04
| Create Database schema |  | Apoorv , Pranjay | 2 | bar: 2020-10-01; 2020-10-05
| Maintain Project Journal |  | Pranjay, Swapnil | 4 | bar: 2020-10-08; 2020-10-22; 2020-11-06; 2020-11-29
| UI Wireframe |  | Pranav, Swapnil | 7 | 2020-09-30: 2; 2020-10-10: 2; 2020-10-17: 2; 2020-10-24: 1
| API documentation |  | All | 8 | 2020-10-27: 2; 2020-11-03: 2; 2020-11-10: 2; 2020-11-30: 2
| Power point Presentation |  | Pranav, Pranjay | 2 | 2020-12-04: 2
Sign Up and Login | Sign Up (Frontend) |  | Pranav,Swapnil | 4 | 2020-10-02: 2; 2020-10-06: 2
| Login(Frontend) | 1 | Pranav,Swapnil | 4 | 2020-10-03: 2; 2020-10-10: 2
| Sign Up (Backend) | 1 | Apoorv , Pranjay | 4 | 2020-10-01: 2; 2020-10-05: 2
| Login(Backend) | 1 | Apoorv , Pranjay | 4 | 2020-10-02: 2; 2020-10-09: 2
Admin | Approve and Reject (Frontend) | 2 | Pranav,Swapnil | 4 | 2020-10-13: 2; 2020-10-17: 2
| Approve and Reject (Backend) | 2 | Apoorv , Pranjay | 4 | 2020-10-10: 2; 2020-10-16: 2
User | Get favorite search(Frontend) | 11 | Pranav,Swapnil | 4 | 2020-11-22: 2; 2020-11-27: 2
| Get favorite home(Frontend) | 12 | Pranav,Swapnil | 4 | 2020-11-25: 2; 2020-11-28: 2
| Get application status (Frontend) | 13 | Pranav,Swapnil | 3 | 2020-11-24: 2; 2020-11-30: 1
| My properties (Frontend) | 14 | Pranav | 4 | 2020-12-03: 2; 2020-12-05: 2
| Get favorite search(Backend) | 11 | Apoorv , Pranjay | 4 | 2020-11-16: 2; 2020-11-23: 2
| Get favorite home(Backend) | 12 | Apoorv , Pranjay | 4 | 2020-11-18: 2; 2020-11-25: 2
| Get application status (Backend) | 13 | Apoorv , Pranjay | 3 | 2020-11-27: 2; 2020-12-02: 1
| My properties (Backend) | 14 | Apoorv , Pranjay | 4 | 2020-11-28: 2; 2020-12-04: 2
Property | Show property (Frontend) | 6 | Pranav,Swapnil | 4 | 2020-11-02: 2; 2020-11-03: 2
| Edit property (Frontend) | 7 | Pranav,Swapnil | 4 | 2020-11-06: 2; 2020-11-09: 2
| Delete property (Frontend) | 8 | Pranav,Swapnil | 4 | 2020-11-10: 2; 2020-11-14: 2
| Add to favorite (Frontend) | 9 | Pranav | 2 | 2020-11-10: 2
| Apply for the property (Frontend) | 10 | Swapnil | 4 | 2020-11-17: 2; 2020-11-20: 2
| Review application (Frontend) | 15 | Pranav,Swapnil | 4 | 2020-11-19: 2; 2020-11-21: 2
| Show property (Backend) | 6 | Apoorv , Pranjay | 4 | 2020-10-27: 2; 2020-10-30: 2
| Edit property (Backend) | 7 | Apoorv , Pranjay | 4 | 2020-10-29: 2; 2020-11-02: 2
| Delete property (Backend) | 8 | Apoorv , Pranjay | 2 | 2020-11-03: 2
| Add to favorite (Backend) | 9 | Apoorv , Pranjay | 4 | 2020-11-04: 2; 2020-11-12: 2
| Apply for the property (Backend) | 10 | Apoorv , Pranjay | 4 | 2020-11-06: 2; 2020-11-12: 2
| Review application (Backend) | 15 | Apoorv , Pranjay | 4 | 2020-11-13: 2; 2020-11-14: 2
Listing | Add listing (Frontend) | 3 | Pranav,Swapnil | 4 | 2020-10-14: 2; 2020-10-22: 2
| Show all listings (Frontend) | 4 | Pranav,Swapnil | 4 | 2020-10-16: 2; 2020-10-23: 2
| Apply filters (Frontend) | 5 | Pranav,Swapnil | 4 | 2020-10-28: 2; 2020-10-30: 2
| Add listing (Backend) | 3 | Apoorv , Pranjay | 4 | 2020-10-12: 2; 2020-10-19: 2
| Show all listings (Backend) | 4 | Apoorv , Pranjay | 4 | 2020-10-15: 2; 2020-10-21: 2
| Apply filters (Backend) | 5 | Apoorv , Pranjay | 4 | 2020-10-24: 2; 2020-10-27: 2
Cloud Deployment | Deploy the project on cloud | 5 | Apoorv , Pranav | 4 | 2020-10-24: 2; 2020-10-27: 2
Team:
Apoorv | 4 hours / Week
Pranjay | 4 hours / Week
Pranav | 4 hours / Week
Swapnil | 4 hours / Week
Total Available Hours for Weekly Sprints: | 16
Total Available Hours for the Project: | 160