## Sprint
|  |  |  | Week #1 (16 hrs / week) | [6 empty] | Week #2 (16 hrs / week) | [6 empty] | Week #3 (16 hrs / week) | [6 empty] | Week #4 (16 hrs / week) | [6 empty] | Week #5 (16 hrs / week) | [6 empty] | Week #6 (16 hrs / week) | [6 empty] | Week #7 (16 hrs / week) | [6 empty] | Week #8 (16 hrs / week) | [6 empty] | Week #9 (16 hrs / week) | [6 empty] | Week #10 (16 hrs / week)
Backlog Item | Task | Task Owner | Initial Estimate (Total Sprint Hours = 16 x 10) | D1 | D2 | D3 | D4 | D5 | D6 | D7 | D8 | D9 | D10 | D11 | D12 | D13 | D14 | D15 | D16 | D17 | D18 | D19 | D20 | D21 | D22 | D23 | D24 | D25 | D26 | D27 | D28 | D15 | D16 | D17 | D18 | D19 | D20 | D21 | D22 | D23 | D24 | D25 | D26 | D27 | D28 | D15 | D16 | D17 | D18 | D19 | D20 | D21 | D22 | D23 | D24 | D25 | D26 | D27 | D28 | D15 | D16 | D17 | D18 | D19 | D20 | D21 | D22 | D23 | D24 | D25 | D26 | D27 | D28
 | time axis 2020-09-27 to 2020-12-05
|  |  |  | 160 | 157.7143 | 155.4286 | 153.1429 | 150.8571 | 148.5714 | 146.2857 | 144 | 141.7143 | 139.4286 | 137.1429 | 134.8571 | 132.5714 | 130.2857 | 128 | 125.7143 | 123.4286 | 121.1429 | 118.8571 | 116.5714 | 114.2857 | 112 | 109.7143 | 107.4286 | 105.1429 | 102.8571 | 100.5714 | 98.2857 | 96 | 93.7143 | 91.4286 | 89.1429 | 86.8571 | 84.5714 | 82.2857 | 80 | 77.7143 | 75.4286 | 73.1429 | 70.8571 | 68.5714 | 66.2857 | 64 | 61.7143 | 59.4286 | 57.1429 | 54.8571 | 52.5714 | 50.2857 | 48 | 45.7143 | 43.4286 | 41.1429 | 38.8571 | 36.5714 | 34.2857 | 32 | 29.7143 | 27.4286 | 25.1429 | 22.8571 | 20.5714 | 18.2857 | 16 | 13.7143 | 11.4286 | 9.1429 | 6.8571 | 4.5714 | 2.2857 | Ideal Burndown
|  |  | 160 | 2020-09-27: 160; 2020-09-28: 158; 2020-09-29: 154; 2020-09-30: 152; 2020-10-01: 152; 2020-10-02: 148; 2020-10-03: 146; 2020-10-04: 146; 2020-10-05: 142; 2020-10-06: 140; 2020-10-07: 136; 2020-10-08: 134; 2020-10-09: 130; 2020-10-10: 130 | Remaining Hrs (Total)
Initial Documentation | Create the Class Diagram | Apoorv , Pranjay | 8 | 2020-09-29: 2; 2020-10-02: 2; 2020-10-05: 2; 2020-10-08: 2
| Create Project TaskBoard with known Tasks on GitHub | Swapnil | 4 | 2020-10-02: 2; 2020-10-09: 2
| Create Architecture Diagram | Pranav | 8 | 2020-09-30: 2; 2020-10-03: 2; 2020-10-05: 2; 2020-10-07: 2
| Create SCRUM sheet | Swapnil | 4 | 2020-09-28: 2; 2020-09-29: 2
| Create README file | Swapnil | 4 | 2020-10-07: 2
| Create Database schema | Apoorv , Pranjay | 8 | 2020-10-06: 2; 2020-10-09: 2
| Create UI Wireframe | Pranav, Swapnil | 8
Database Design |  | Apoorv , Pranjay | 20
|  | Pranjay | 20
40
Signup/ Login Portal |  | Pranav | 10
|  | Swapnil | 10
|  | Pranav,Swapnil | 20
Team:
Apoorv | 4 hours / Week
Pranjay | 4 hours / Week
Pranav | 4 hours / Week
Swapnil | 4 hours / Week
Total Available Hours for Weekly Sprints: | 16
Total Available Hours for the Project: | 160